## PRN221_NET1706_Group2
Overall Project
Group Name: | Group 2 |  | Note : -
Max Mark :
Student Percent (%) | 100%
Teacher Percent (%) | 0%
No | Student ID | Student Name | Class Name | Student Percent | Teacher Percent (%) | Mark | Note
1 | SE171391 | Trần Đình Minh Quang | NET1706 | 29% |  | #DIV/0!
2 | SE171507 | Bùi Duy Anh | NET1706 | 27% |  | #DIV/0!
3 | SE171552 | Lê Hoàng Sơn | NET1706 | 24% |  | #DIV/0!
4 | SE171442 | Nguyễn Đặng Phương Nam | NET1706 | 20% |  | #DIV/0!

## Test Task
Task List
No | Task Name | Percent (%) | Student Name | Deadline | Created At | Updated At | Status | Note
1 | Draw database ERD | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
2 | Draw class diagram | 100% | Duy Anh | 2024-06-15 | 2024-06-10 |  | Done
3 | Write document | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
4 | Create base project | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
5 | Update document | 100% | Duy Anh | 2024-06-15 | 2024-06-10 |  | Done
6 | Home Page View | 100% | Hoàng Sơn | 2024-06-15 | 2024-06-10 |  | Done
7 | Login Page | 100% | Phương Nam | 2024-06-15 | 2024-06-10 |  | Done
8 | Login View | 100% | Hoàng Sơn | 2024-06-15 | 2024-06-10 |  | Done
9 | Login service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
10 | Register page | 100% | Phương Nam | 2024-06-15 | 2024-06-10 |  | Done
11 | Register view | 100% | Hoàng Sơn | 2024-06-15 | 2024-06-10 |  | Done
12 | Register service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
13 | Pet List Page | 100% | Duy Anh | 2024-06-15 | 2024-06-10 |  | Done
14 | Get Pet List service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
15 | Create Pet Page | 100% | Duy Anh | 2024-06-15 | 2024-06-10 |  | Done
16 | Create Pet service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
17 | Get Service list Service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
18 | Create Service service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
19 | Show Time Slot Service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
20 | Book Appointment Service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
21 | Book Appointment Page View | 100% | Duy Anh | 2024-07-26 | 2024-06-10 |  | Done
22 | Transaction Page View | 100% | Duy Anh | 2024-07-10 | 2024-06-10 |  | Done
23 | Transaction list service | 100% | Minh Quang | 2024-06-20 | 2024-06-10 |  | Done
24 | Transaction create service | 100% | Minh Quang | 2024-06-20 | 2024-06-10 |  | Done
25 | Transaction update payment status service | 100% | Minh Quang | 2024-06-20 | 2024-06-10 |  | Done
26 | Transaction get by id service | 100% | Minh Quang | 2024-06-20 | 2024-06-10 |  | Done
27 | Appointment List View | 100% | Duy Anh | 2024-06-30 | 2024-06-10 |  | Done
28 | Get appointment by id service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
29 | Appointment List Service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
30 | Appointment Filter Service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
31 | Appointment Update Status Service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
32 | Appointment cancel service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
33 | Staff dashboard | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
34 | Staff get list appointment page | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
35 | Staff get details appointment page | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
36 | Staff update appointment transaction page | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
37 | Staff get list transaction | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
38 | Pet Detail View | 100% | Duy Anh | 2024-06-30 | 2024-06-10 |  | Done
39 | Update pet service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
40 | Delete pet service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
41 | Get pet by id service | 100% | Minh Quang | 2024-06-15 | 2024-06-10 |  | Done
42 | Customer Appointment List Page | 100% | Duy Anh | 2024-06-30 | 2024-06-10 |  | Done
43 | Customer Appointment Detail Page | 100% | Duy Anh | 2024-06-30 | 2024-06-10 |  | Done
44 | Pet Create Page | 100% | Duy Anh | 2024-06-30 | 2024-06-10 |  | Done
45 | Add Service Page | 100% | Hoàng Sơn | 2024-06-15 | 2024-06-10 |  | Done
46 | Update Service Page | 100% | Hoàng Sơn | 2024-06-15 | 2024-06-10 |  | Done
47 | View Service Page | 100% | Hoàng Sơn | 2024-06-15 | 2024-06-10 |  | Done
48 | Vet View Time Table Page | 100% | Hoàng Sơn | 2024-07-10 | 2024-06-10 |  | Done
49 | Vet Add Medical Record | 100% | Hoàng Sơn | 2024-07-10 | 2024-06-10 |  | Done
50 | Pet Edit Page | 100% | Duy Anh | 2024-06-30 | 2024-06-10 |  | Done
51 | Pet Delete Page | 100% | Duy Anh | 2024-06-30 | 2024-06-10 |  | Done
52 | Add Paging to Vet Appointments Page | 100% | Hoàng Sơn | 2024-07-10 | 2024-06-10 |  | Done
53 | Transaction Page | 100% | Duy Anh | 2024-07-10 | 2024-06-10 |  | Done
54 | Transaction view List | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
55 | staff transaction view details | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
56 | admin dashboard | 100% | Phương Nam | 2024-07-10 | 2024-06-10 |  | Done
57 | Get list medical record service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
58 | Get medical record by id service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
59 | Get all medical items service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
60 | Create medical item service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
61 | Create user with any role by admin service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
62 | Get users by role service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
63 | Create hospitalization service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
64 | Get list hospitalizations service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
65 | Get hospitalizations by id service | 100% | Minh Quang | 2024-07-10 | 2024-06-10 |  | Done
66 | Get configuration list service | 100% | Minh Quang | 2024-07-11 | 2024-06-10 |  | Done
67 | Staff Create Appointment | 100% | Duy Anh | 2024-07-11 | 2024-06-10 |  | Done
68 | Customer Cancel Appointmet Page | 100% | Duy Anh | 2024-07-11 | 2024-06-11 |  | Done
69 | Filter transaction service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
70 | Filter appointment service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
71 | Update user service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
72 | View profile | 100% | Phương Nam | 2024-07-11 | 2024-06-28 |  | Done
73 | VnPay service | 100% | Phương Nam | 2024-07-11 | 2024-06-28 |  | Done
74 | VnPay create transaction page | 100% | Duy Anh | 2024-07-11 | 2024-06-28 |  | Done
75 | Get all available cage service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
76 | Staff create hospitalization time page | 100% | Hoàng Sơn | 2024-07-11 | 2024-06-28 |  | Done
77 | Vet update hospitalization page | 100% | Hoàng Sơn | 2024-07-11 | 2024-06-28 |  | Done
78 | Update medical item service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
79 | Delete medical item service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
80 | Update service service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
81 | Delete service service | 100% | Minh Quang | 2024-07-11 | 2024-06-28 |  | Done
82 | Admin CRUD service page | 100% | Phương Nam | 2024-07-11 | 2024-06-28 |  | Done
83 | Admin CRUD medical item page | 100% | Phương Nam | 2024-07-11 | 2024-06-28 |  | Done
84 | View pet medical record page | 100% | Duy Anh | 2024-07-11 | 2024-06-28 |  | Done
85 | Staff view medical record page | 100% | Hoàng Sơn | 2024-07-11 | 2024-06-28 |  | Done
86 | Admin service list view | 100% | Hoàng Sơn | 2024-07-11 | 2024-06-28 |  | Done
87 | Admin medical item view | 100% | Hoàng Sơn | 2024-07-11 | 2024-06-28 |  | Done